© BuyReadySite.com

# SCL Capital — Master M1/M2 Delivery Checklist

Дата обновления: 2026-05-04

## Progress Dashboard

Этот файл является главным рабочим чеклистом по текущему объединенному scope: M1: Pipeline v2 + Login/Auth и M2: Campaigns/Lead Doc. Процент готовности обновляется после каждого завершенного блока и после каждого testing gate.

| Направление | Вес | Готовность | Статус |
| --- | --- | --- | --- |
| Phase 0 — Scope consolidation и source map | 6% | 6% | Done |
| M1.1 — Passwordless OTP Login/Auth | 10% | 9.5% | Live SMS OTP + browser redirect/current-user passed; Resend email fallback blocked by missing production config |
| M1.2 — Pipeline v2 base parity | 12% | 12% | Done — stage/visual/scope/metrics/search/drag-drop gates verified |
| M1.3 — Pipeline card/panel/modals parity | 12% | 12% | Done — card/panel/modal/context-menu/browser gates verified |
| M1.4 — Pipeline AI extractor + badges | 14% | 6% | Inbox AI repair + owner-action reclassification gate passed; dedicated Pipeline extractor backend pending |
| M1.5 — Auto-nurture attempt mechanic | 10% | 10% | Done — attempt mechanic, UI, reset paths, manual override, browser/pixel, Revive gate |
| M1.6 — M1 regression, pixel-close, release gate | 8% | 8% | Done — functional and visual gates verified; full-env suite limitation remains documented |
| M2.1 — Leads/Campaign access + source fixes | 8% | 7% | API scope tests/build + mocked admin/rep browser smoke passed; live two-rep CSV smoke still pending |
| M2.2 — Leads enrichment columns + export | 8% | 7% | Enrichment/export tests/build + browser/responsive/export-column evidence passed; strict pixel-close still pending |
| M2.3 — AI Retarget campaigns | 8% | 8% | Done — LeadCohort DB/cache/cron, Build modal/list/actions, prod DB/health, and retained prototype compare passed |
| M2.4 — M2 regression, pixel-close, release gate | 4% | 2% | Focused M2 API regression, root build, and mocked Leads/Campaigns UI smoke for filters/import/add/create/actions passed |
| Overall | 100% | 87.5% | M2.3 complete; M2.4 functional bootstrap passed; Resend config, Pipeline extractor, M2.1/M2.2 live/pixel gaps remain |

## Source Map

### M1 sources

- scl-pipeline-ai-handoff/extractor-spec.md — canonical behavior spec для Pipeline AI extractor.

- scl-pipeline-ai-handoff/scl_pipeline_v11.html — binding visual target только для retained v1 Pipeline AI / auto-nurture elements.

- scl-pipeline-ai-analysis/MASTER_WORK_CHECKLIST.md — предыдущий детальный checklist по Pipeline AI.

- scl-pipeline-ai-handoff/M1/SCL_Auth_login.pdf — canonical M1 auth/login source: passwordless OTP replacement.

- archive/PIPELINE_AUDIT.md — старый audit Pipeline prototype vs React implementation.

- scl-pipeline-phase2.pdf — Pipeline replacement / Command Center / auth milestone document.

- Phasse 2/SCL_Milestones.pdf — milestone acceptance для Pipeline + auth.

- CHECKLIST_M1_M2_REMEDIATION_2026-04-28.md — production cleanup, auth/security, M2 inbox/follow-up evidence.

### M2 sources

- CHECKLIST_LEADS_CAMPAIGNS.md — предыдущий Leads + Campaigns checklist.

- SCL_Leads_Campaigns_Refinement.pdf — оригинальный Leads/Campaigns refinement source.

- scl-pipeline-ai-handoff/m2/PHASE3_COMPLEXITY_BRIEF.pdf — M2 Phase 3 complexity/value brief for AI Suggested Campaigns.

- Prototype: https://papaya-swan-76d714.netlify.app/scl_leads_campaigns_scope_v3.html.

- Current M2 prototype scope: 4 fixes only:

  - Phase 1: reps see only leads they uploaded; reps see only campaigns they created.

  - Phase 2.1: Source column shows readable list name, not UUID.

  - Phase 2.2-6: Industry + Revenue + Last Contact + Export CSV, wired from AI classifier and existing data.

  - Phase 3: AI Retarget suggestions and AI-built campaign lineage in All Campaigns.

### Explicitly out of scope for M2 unless separately approved

- Cohort bar outside the shown AI Retarget Suggestions area.

- Suppressed leads zone.

- List management rebuild.

- Multi-owner / multi-rep ownership for Leads/Campaigns.

- Full Leads tab rebuild beyond the prototype’s retained table/filter/export scope.

- Gmail extension or email sending from SCL.

## Non-Negotiable Rules

- Не трогать боковое меню при M2 Leads/Campaigns styling, кроме случаев явного bug fix.

- Перед каждым изменением фиксировать affected files и regression surface.

- После каждой фазы выполнять focused testing gate.

- После каждого UI-блока выполнять pixel-close сравнение с relevant prototype.

- Если текущие стили не применяются к M2, создать новый scoped style set для Leads/Campaigns section, не ломая глобальные tokens и sidebar.

- Не перетирать manual rep values AI suggestions.

- Не запускать auto-stage / auto-nurture behavior без audit trail и rollback-safe validation.

- Не делать silent data migrations, destructive SQL, reset, truncate или delete production data.

- Не коммитить .env, токены, prod dumps, screenshots с секретами.

- Все user-facing changes проверять как admin и как rep.

- Все auth/permission changes проверять negative cases: чужие leads, чужие campaigns, чужие deals.

## Client Pain Points To Guard

- Login page must match the attached SCL visual contract: typography, dark HUD frame, metallic SCL wordmark, spacing, gradient button, phone verification footer, and SCL Systems footer.

- Platform access must be smoked before reps become active: /api/health, /login, database, Redis.

- Local QA needs a controlled dev_mode_login path so testers can enter the app without waiting for SMS/email OTP.

- dev_mode_login must never be available in production, even if env flags are accidentally set.

- AI suggestions должны соответствовать последнему client message и full-thread context.

- Email CTA должен брать email из conversation/client text прежде lead-list email.

- Gmail compose должен открываться надежно и только с to= без subject/body.

- Follow-up suggestions не должны ставить 5 AM или quiet-hours-conflicting times.

- Quiet hours должны блокировать отправку корректно, но UI должен объяснять причину.

- Inbound conversation owner не должен самопроизвольно переassignиваться на текущего пользователя.

- Reps не должны видеть чужие leads/campaigns/deals без явного права.

- Source column не должен показывать UUID там, где нужен readable list/campaign name.

- Export CSV должен учитывать текущие filters и не выгружать чужие данные rep-у.

- UI не должен выглядеть как “почти похоже”: retained prototype elements сравниваются pixel-close.

- Inbox action row must preserve existing buttons: Mark Interested, Not Interested, DNC, Email Rcv, Add to Pipeline, Follow-Up, Mark Unread/Note where present, and Assign Rep where role-allowed.

- Inbox CONTACT tab must preserve structured Assigned Rep field.

- Rep chip/avatar must remain visible on cards where assignment exists in both Admin and My Convs views.

- Admin/My Convs scope must remain unchanged: admins/managers can toggle; reps are locked to My Convs; totals follow the selected scope.

- Pipeline AI must never write or infer Deal.assignedRepId / Deal.assistingRepIds; badges are deal-level facts and must respect existing rep scope.

- Deal sharing must remain unchanged: primary rep can add assisting reps without admin involvement.

- Auto-reassignment between reps is explicitly out of scope.

## Phase 0 — Scope Consolidation And Setup

- Собрать M1 sources.

- Собрать M2 sources.

- Прочитать новые папки handoff: scl-pipeline-ai-handoff/M1 и scl-pipeline-ai-handoff/m2.

- Зафиксировать SCL_Auth_login.pdf как M1 auth source.

- Зафиксировать PHASE3_COMPLEXITY_BRIEF.pdf как M2 AI Retarget complexity source.

- Проверить старые чеклисты: Pipeline AI, M1/M2 remediation, Leads/Campaigns.

- Открыть и прочитать M2 prototype scl_leads_campaigns_scope_v3.html.

- Зафиксировать, что M2 prototype содержит только 4 shipping changes.

- Зафиксировать M1 Pipeline v11 retained visual elements.

- Создать evidence folder для новых M1/M2 работ без секретов.

- Создать baseline screenshots текущих страниц до изменений:

  - Login page;

  - Pipeline simple mode;

  - Pipeline execution mode;

  - Deal card;

  - Deal panel;

  - Leads tab admin view;

  - Leads tab rep view;

  - Campaigns tab admin view;

  - Campaigns tab rep view.

- Снять baseline browser console errors для этих страниц.

- Снять baseline API responses shape для affected endpoints.

### Phase 0 Gate

- Все source artifacts зафиксированы в checklist.

- Есть до-скриншоты и console baseline.

- Есть список affected files.

- Overall progress обновлен.

## M1.1 — Passwordless OTP Login/Auth

### Implementation evidence — 2026-05-02

- Auth code map completed before implementation: current auth was password-only, User.mobilePhone exists, Twilio config exists, Resend/email sender needed env config.

- Prisma OTP schema added: OtpChannel, LoginOtp, user failed-attempt and lockout fields.

- Backend OTP service added with hashed 6-digit codes, 5-minute expiry, one-time use, prior-code invalidation, SMS default and email fallback.

- Public endpoints added: POST /api/auth/request-otp, POST /api/auth/verify-otp.

- Admin unlock endpoint added: POST /api/auth/users/:id/unlock-otp.

- Login UI converted to passwordless email -> OTP flow while preserving SCL visual style.

- Login UI redesigned to match the SCL Auth target: SCL wordmark, SALES COMMAND LAYER, COMMAND YOUR PIPELINE, EXECUTION. FOCUS. RESULTS., SIGN IN TO SCL, email field, blue SEND CODE, phone verification note, and SCL Systems footer.

- Login visual styling is scoped under .scl-auth in client/src/styles/globals.css to avoid sidebar/dashboard regressions.

- Admin Users UI now shows OTP locked status and clear-lock action.

- Password /api/auth/login endpoint intentionally preserved as fallback until demo/JB approval.

- Account enumeration reduced: request-code response is generic for missing/inactive/missing-phone accounts.

- Wrong OTP attempts 1-4 return remaining-attempts messaging; 5th failed attempt locks account for 30 minutes.

- Local validation passed: Prisma Client generation, backend build, frontend build, DB-free OTP policy tests, production-preview login UI check.

- Browser validation passed for auth UI: desktop preview, mobile-width preview, server-unavailable state, and mocked email -> OTP -> verify -> REP /pipeline redirect.

- Frontend CSS minify warning fixed by replacing the problematic light-mode combo selector with :is() selectors.

- Production MySQL schema sync completed on app.sclcapital.io via reviewed additive SQL after DB backup.

- Production Redis availability verified through /api/health after deploy restart.

- Live SMS OTP delivery validation passed on production: Twilio message delivered, /api/auth/verify-otp returned JWT/refresh token, latest LoginOtp row was consumed, and /api/auth/me returned the ADMIN user.

- Live browser OTP flow passed on production: /login -> Send code -> OTP state -> real SMS code verify -> /command-center redirect; fresh hard navigation loaded Command Center successfully.

- Resend email delivery validation remains blocked: production /api/auth/request-otp with channel=email returns 503 Email sign-in fallback is not configured because RESEND_API_KEY / RESEND_FROM_EMAIL are missing.

- Deployment note completed: production DB backup saved, additive schema sync applied, Prisma Client regenerated, and production build passed.

### Dev mode login gate — 2026-05-04

- Added POST /api/auth/dev-login for local QA login without OTP code.

- Backend dev login requires DEV_MODE_LOGIN_ENABLED=true and is disabled by default.

- Backend blocks dev login when NODE_ENV=production, even if DEV_MODE_LOGIN_ENABLED=true is accidentally set.

- Optional DEV_MODE_LOGIN_SECRET support added for shared non-production environments.

- Dev login rejects missing/inactive users, updates lastLoginAt, invalidates user cache, and returns the same JWT/refresh session shape as OTP login.

- Login UI shows Dev mode login only when VITE_DEV_MODE_LOGIN_ENABLED=true and import.meta.env.PROD is false.

- Production bundle/preview verified: Dev mode login button count is 0; OTP Send code remains visible.

- Production deploy/smoke passed on 98ac6be8d: /api/health database/Redis ok, / 200, /login 200, /api/auth/dev-login 404, live UI dev button count 0.

- Env docs updated: server/.env.example, .env.production.example, and client/.env.example.

- Focused auth regression passed: authDevModeLogin, authOtpPolicy, clientPreservationRequirements — 11/11 tests.

- Root production build passed after dev login changes: server tsc plus client tsc && vite build.

- Evidence JSON added: audit-screenshots/dev-mode-login-evidence.json.

### Scope decision

- Implement passwordless OTP as primary login flow.

- Preserve existing password-based /api/auth/login fallback for production safety until demo/JB approval.

- Confirm all 6 reps + admin have populated account email and mobilePhone values.

- Confirm Twilio 10DLC can handle OTP volume of ~50-100/day peak.

- Confirm Resend is configured for SCL-branded OTP sender. Blocked 2026-05-04: production email OTP returns 503 until RESEND_API_KEY and RESEND_FROM_EMAIL are configured.

- Confirm old password column may only be dropped after demo pass and explicit JB approval.

- Redirect mapping implemented:

  - admin/manager -> current Dashboard surface /command-center;

  - rep -> /pipeline.

### Login screen behavior

- Match the M1 SCL auth visual target while preserving passwordless OTP behavior.

- Keep email field as account identifier.

- Replace password input flow with SEND CODE flow.

- Send OTP via SMS to account mobilePhone by default.

- Same screen transitions into 6-digit OTP entry state.

- OTP entry state matches existing login aesthetic.

- On success, redirect by role.

- Error states are clear and avoid account/phone enumeration on request-code.

- Loading states for send code and verify code.

- Resend code state respects countdown/rate-limit responses.

- Keyboard flow works: email -> send -> OTP digits -> submit.

- OTP input supports paste of 6-digit code.

- OTP input rejects non-numeric characters.

- Dev-only login button can bypass OTP in local QA only and is hidden in production builds.

### Backend OTP model and storage

- Decide storage model: DB-backed LoginOtp table with user lock fields.

- Store OTP codes hashed, never plaintext.

- Store expiration timestamp.

- Store used/consumed status and invalidate after successful verification.

- Requesting a new OTP invalidates prior unused OTPs for that user.

- OTP compare uses bcrypt hash verification.

- Do not log OTP codes.

- Do not return OTP codes in API responses.

- Add audit fields for request channel, user id, destination hash/masked destination, createdAt, consumedAt, expiresAt.

- Cleanup/expiry policy for old OTP records if DB-backed.

### Safeguard 1 — failed OTP lockout

- Track failed OTP attempts per account in rolling 15-minute window.

- Wrong OTP attempts 1-4 return decreasing N attempts remaining message.

- 5th wrong OTP within rolling 15 minutes locks account for 30 minutes.

- Locked account cannot verify OTP.

- Locked account cannot request new SMS OTP.

- Locked account cannot request new email fallback OTP.

- Lockout counter is shared across SMS and email OTP.

- After 30 minutes, account auto-unlocks and attempt counter resets to zero.

- Admin can manually unlock user from Users admin panel before 30 minutes expires.

- Unlock event writes auth audit log.

### Safeguard 2 — OTP expiration and one-time use

- OTP expires 5 minutes after generation.

- Code submitted after expiry is rejected as expired/generic invalid.

- Successfully verified OTP cannot be reused.

- Second verification attempt with same code is rejected.

- New OTP request invalidates older unused code for that user.

- Expired/used/invalidated codes produce safe generic errors.

### Safeguard 3 — OTP request rate limits

- Max 3 SMS OTP sends per phone number per rolling 1-hour window.

- 4th SMS OTP request within 1 hour is blocked.

- Blocked response includes Too many requests with retry seconds/time.

- Frontend shows live countdown for blocked resend.

- After 1 hour from oldest send, counter resets.

- SMS sends and email fallback sends have independent 3/hour limits.

- Rate limits cannot be bypassed by switching email casing.

- Rate limits use normalized phone/email keys.

- Rate limit events are logged without secrets.

### Safeguard 4 — email fallback for phone loss

- Add link below SEND CODE: Lost access to your phone? Use email instead.

- Link is visible for all users.

- Clicking sends OTP to account email.

- Email OTP arrives within 30 seconds in test/demo conditions. Blocked by missing production Resend config.

- Email OTP uses same 5-minute expiration.

- Email OTP uses same 5-attempt lockout counter as SMS.

- Email OTP request uses separate 3/hour email fallback rate limit.

- Email subject: SCL Capital · Your sign-in code.

- Email body is SCL-branded and does not expose extra account info.

### Existing auth hardening compatibility

- Проверить server/src/controllers/authController.ts на login, register, current user, update user.

- Проверить server/src/routes/auth.ts на middleware и role gates.

- Проверить server/src/middleware/auth.ts на JWT parsing, expired token, missing token, malformed token.

- Проверить localStorage behavior в frontend auth flow.

- Проверить, что production errors не возвращают stack traces.

- Проверить, что NODE_ENV=production не допускает localhost CLIENT_URL / WEBHOOK_BASE_URL.

- Проверить refresh/current-user flow после reload в live backend/browser session: live OTP token returned /api/auth/me 200, and cache-busted /command-center navigation loaded the authenticated admin shell.

- Проверить 401 vs 403 semantics:

  - unauthenticated -> 401;

  - authenticated wrong role/scope -> 403 или 404 там, где нужно скрыть resource existence.

### Frontend auth integration

- Проверить client/src/pages/LoginPage.tsx.

- Проверить client/src/stores/authStore.ts.

- Исправить/проверить известный риск: 5xx не должен навсегда блокировать re-auth.

- Проверить loading state login form.

- Проверить invalid credentials state.

- Проверить server unavailable state.

- Проверить redirect after login with real OTP success.

- Проверить logout clears sensitive state in auth store.

- Проверить protected route redirect.

- Проверить role-based initial route mapping:

  - admin -> allowed admin/default surface;

  - rep -> own scoped surfaces only.

### M1.1 Testing Gate

- Unit/backend tests for auth middleware.

- Unit/backend tests for dev-mode login production guard and optional dev key.

- Unit/backend tests for OTP generation, hash storage, expiration, reuse rejection.

- Unit/backend tests for rolling failed-attempt lockout.

- Unit/backend tests for OTP destination normalization/masking and send rate-limit helper.

- Unit/backend tests for SMS/email normalized rate-limit policy helper.

- Unit/backend tests for admin unlock.

- API manual tests:

  - send SMS OTP success;

  - verify OTP success;

  - wrong OTP 4 times shows remaining attempts;

  - wrong OTP 5th time locks account;

  - locked account cannot request new OTP;

  - expired OTP rejected;

  - used OTP rejected;

  - new OTP invalidates old OTP;

  - 4th SMS OTP in 1 hour blocked;

  - email fallback OTP success;

  - SMS/email rate limits independent;

  - /api/auth/me without token;

  - expired/malformed token;

  - rep trying admin-only action.

- Browser tests:

  - ☒ login page desktop;

  - ☒ login page half-screen width;

  - ☒ email -> send code -> OTP state;

  - OTP paste;

  - email fallback link;

  - lockout UI;

  - resend countdown UI;

  - ☒ role redirect after mocked OTP login;

  - reload after login;

  - logout.

- Live demo acceptance from PDF passes in one flow.

- Console errors: none.

- Auth regression evidence saved.

- Backend build passed after OTP implementation.

- Frontend build passed after OTP implementation.

- Production preview login page rendered correctly.

- Production preview server-unavailable error state shows friendly message.

- Production preview confirms dev-mode login UI is hidden while OTP UI remains visible.

- Progress dashboard updated.

## M1.2 — Pipeline v2 Base Parity

### Implementation evidence — 2026-05-02

- Verified v2 stage labels in PipelinePageV2, DealPanel, dealController, leadController, inboxController, dashboardController, commandCenterController.

- Confirmed old audit mismatches are fixed in v2 runtime: ENGAGED_INTERESTED -> Engaged / Interested, QUALIFIED -> Qualified, APPROVED_OFFERS -> Approved / Offers.

- Updated stale Pipeline CSS stage comment from legacy Contacted/New Business vocabulary to current M1.2 stage language.

- Simple mode now hides CLOSED column while execution mode keeps it available.

- Browser mock validation passed: Simple mode columns = 8 without Closed; Execution mode columns = 9 with Closed.

- Browser mock validation passed: search no-match zeroes visible stage counts and clearing search restores board counts.

- Extracted shared deal scope policy for Pipeline + Command Center metrics.

- Guarded /api/deals/board?teamView=true and /api/deals/stats?teamView=true so non-admin users remain scoped to their own/shared deals.

- Default rep Pipeline board now requests primary + explicitly shared/assisting deals; Shared filter still isolates assisting deals in UI.

- Added dealScopePolicy unit tests for admin unscoped team view, rep scoped team view, primary-only filters, shared deal visibility, and funding-event scope.

- Verified stage colors against archive/PIPELINE_AUDIT.md and aligned per-stage .col-bar opacity values.

- Confirmed APPROVED_OFFERS and COMMITTED_FUNDING both use active pipeline nb-col / pipe classes.

- Browser computed-style validation passed for all 9 stage bar colors/opacity values, including Committed 0.85 opacity.

- Browser validation passed: business/contact search terms filter visible cards and execution mode keeps all 9 header totals/count rows.

- Browser validation passed: drag/drop works with and without active search filter and uses the underlying board stage safely.

- Screenshot comparison completed for Simple and Execution modes: audit-screenshots/m1-2-pipeline-simple.png, audit-screenshots/m1-2-pipeline-execution.png.

- Controller-level negative tests passed: REP teamView=true remains scoped; ADMIN teamView=true can access unscoped board.

- Verification passed: npm run build and cd server && npx vitest run tests/dealScopePolicy.test.ts tests/dealControllerScope.test.ts.

- Legacy pipelineStage seed/old /pipeline/stages lead-board path left unchanged by decision: current M1.2 v2 route uses /api/deals/board; legacy data cleanup is separate scope.

### Stage system and board structure

- Verify exact 9 stage list and labels:

  - New Lead;

  - Engaged / Interested;

  - Qualified;

  - Submitted (In Review);

  - Approved / Offers;

  - Committed (Funding);

  - Funded;

  - Nurture;

  - Closed.

- Fix mismatch from audit:

  - ENGAGED_INTERESTED label must be Engaged / Interested, not Contacted.

  - QUALIFIED label must be Qualified, not Qualified / Interested.

  - APPROVED_OFFERS label must be Approved / Offers, not New Business.

- Verify stage colors against prototype and archive/PIPELINE_AUDIT.md.

- Add/apply per-stage column bar opacity.

- Ensure APPROVED_OFFERS and COMMITTED_FUNDING both use active pipeline classes.

- Simple mode hides CLOSED column.

- Execution mode shows expected columns and totals.

- Admin view can see all deals.

- Rep view sees own + explicitly shared/assisting deals only.

- Search filters business name and contact/client name.

- Clearing search restores board.

- Drag/drop works only when current filters/search state cannot cause wrong-stage moves.

### Pipeline metrics and totals

- Active Pipeline $ = Approved + Committed only.

- Submitted/In Review amount, if implemented, does not alter Active Pipeline $.

- Funded MTD matches funding events current month.

- Lifetime Funded remains unchanged unless explicitly in scope.

- At Risk logic remains consistent with current business rules.

- Admin Command Center Pipeline Value, if touched, must read Pipeline Value (Approved) and sum Approved deals only.

### Pipeline ownership and sharing

- Verify primary rep ownership.

- Verify assisting reps if supported by current schema/UI.

- Verify All Deals button visible only to admin if prototype requires it.

- Verify shared deals sort below primary deals.

- Verify contact info hidden from unauthorized reps.

- Verify scoped Socket.IO events do not leak deal updates to all users.

### M1.2 Testing Gate

- Admin login -> sees all stage columns and all allowed deals.

- Rep login -> sees only own/shared deals.

- Stage labels match character-for-character.

- Stage colors match prototype tokens.

- Simple mode screenshot compared.

- Execution mode screenshot compared.

- Search works with business name.

- Search works with contact name.

- Drag/drop tested with and without active filters.

- API permission negative tests pass.

- Progress dashboard updated.

## M1.3 — Pipeline Card, Panel, And Modals Parity

### Implementation evidence — 2026-05-02

- DealCard keeps retained hierarchy and now shows readable SMS · list/campaign source from SMS-created client notes.

- Business/contact text selection validated in browser; selecting card text no longer opens panel or starts drag.

- Delete permissions aligned across panel, context menu, and API: admin/manager only; funded deals remain blocked.

- Backend deal-level access checks added for deal detail/update/move/share/call/SMS/funding/renewal action paths.

- deal_events logging verified for stage moves, offers, funded, completed actions, shares, calls, renewal completion, create quick notes, and panel SMS send.

- Browser validation passed for card source chip, panel tabs, modals, context menu close behavior, role matrix, Funding History create/reveal, quick note carryover, and product/revenue controls.

- Server scope tests passed: dealControllerScope.test.ts + dealScopePolicy.test.ts = 10 tests.

- Frontend/client build passed after final layout and selection fixes.

### Deal card parity

- Preserve existing card hierarchy while layering new AI/attempt UI.

- Business name visible and selectable.

- Contact name visible and selectable where allowed.

- Product badge uses prototype .prod-badge visual pattern.

- Product badge + days-in-stage row placement matches prototype.

- Card footer matches prototype:

  - left: rep initials + touched text;

  - right: Age: Nd.

- Review pill appears for Submitted/In Review cards.

- Nurture tags appear on Nurture cards if data exists.

- Nurture urgency pill appears when touch due.

- Source field on deal card populates readable list/campaign source when created from SMS.

- Tooltip preview works in Execution mode only if included in current M1 scope.

- Tooltip hides sensitive contact details from unauthorized users.

### Deal panel parity

- Deal panel opens from card click.

- Conversation tab shows full SMS history.

- Deal + Client tab allows existing editable fields.

- Funding History tab remains functional.

- SMS send bar works from panel where permitted.

- Follow-up scheduler modal exists or current replacement behavior is documented.

- Close/NQ modal exists or current replacement behavior is documented.

- Funded modal exists or current replacement behavior is documented.

- Edit Funding Event modal exists or current replacement behavior is documented.

- New Deal modal creates deal card and reveals it even if filters/search would hide it.

- Quick note on create carries into deal note and activity log if included in scope.

### Context menu

- Right-click opens context menu for allowed users.

- Reps can right-click own/assisted deals only.

- Admin can right-click any non-funded deal.

- Delete is admin-only and blocked for funded deals.

- Move to Nurture opens proper lost/recoverable flow.

- Close/NQ opens proper disqualification flow.

- Share Deal opens ownership/share flow for primary rep/admin.

- Context menu closes on outside click and Escape.

- Every action logs to deal_events.

### M1.3 Testing Gate

- Pixel-close compare: DealCard retained layout.

- Pixel-close compare: DealPanel retained layout.

- Modal screenshots compared to prototype where relevant.

- Text selection works on card names.

- Context menu role matrix tested.

- New deal from Funding History creates and opens the card.

- No regression in existing manual product/revenue controls.

- No console errors.

- Progress dashboard updated.

## M1.4 — Pipeline AI Extractor And Badges

### Implementation evidence — 2026-05-02 B.6 client correction

- Client B.6 correction folded into M1 without schema change: MCA stacked now means 3+ active positions.

- Added typed PipelineAiSignals frontend shape with current_active_positions, has_stacked_history, and recent_stacking_activity.

- Added reusable stacking chip resolver/component for DealCard and DealPanel.

- Implemented chip labels/colors: green 1ST POSITION, yellow 1-POSITION, orange 2-POSITIONS, red {N}-STACKED for count >= 3.

- Implemented active stacking modifier: red pulse and · ACTIVE appended to the rendered base chip.

- Implemented optional debt suffix · $XXXk when total_debt_usd is set and count >= 2.

- Frontend build passed after B.6 chip update.

- Browser mock validation passed: DealCard rendered 1ST POSITION, 1-POSITION, 2-POSITIONS · $180k, 3-STACKED · $240k · ACTIVE; DealPanel rendered active stacked chip.

- Backend extractor/data plumbing still pending: Deal.pipelineAiSignals, Deal.pipelineAiUpdatedAt, and live AI extraction endpoint.

### Client preservation lock — 2026-05-04

- Added B.0 preservation requirement to Pipeline AI specs: Deal.assignedRepId, Deal.assistingRepIds, deal sharing, rep chips, Inbox Assign Rep, CONTACT Assigned Rep, Admin/My Convs scope, and auto-reassignment out of scope.

- Verified current code already preserves the Inbox action-row Assign Rep button for admin/manager assignment workflows.

- Verified current code already renders CONTACT Assigned Rep in the right panel when assignment data exists.

- Verified current code already renders rep chip/avatar on conversation cards where assignment data exists.

- Verified current backend Inbox scope keeps admin/manager Admin View vs My Convs and locks non-admin reps to owned conversations.

- Verified current backend Pipeline scope keeps reps on primary + assisting deals via repScopeFilter and admin/manager unscoped view only.

- Added focused preservation tests so future Pipeline AI work cannot silently remove the client-protected surfaces.

- Restored visible Inbox action-row Mark Unread and Note controls next to the existing assignment/follow-up actions.

- Focused preservation regression passed: clientPreservationRequirements, dealOwnershipPreservation, and dealControllerScope — 11/11 tests.

- Root production build passed after preservation + login visual changes: server tsc plus client tsc && vite build.

- Local production preview /login passed browser validation: HTTP 200, no vertical overflow at 918x667, footer visible in first viewport, SCL visual contract present.

- Production access smoke passed after client escalation: /api/health returned database: ok and redis: ok; live /login returned HTTP 200.

- Evidence JSON added: audit-screenshots/client-preservation-login-access-evidence.json.

### Inbox AI suggestion repair / owner-action gate — 2026-05-04

- AI suggestions now repair stale/generic draft copy against the latest inbound message and full-thread context.

- Deterministic repair covers email shares, amount disclosures, fees/rate/payment questions, credit-score objections, callback logistics, HELOC/LOC clarification, term-range replies, and explicit follow-up windows.

- AI suggestions no longer reuse the client email as the rep sender address in draft copy.

- Conversation detail resolves email priority as texted/conversation email -> lead email -> contact email and passes knownEmail / emailReceived into suggestion repair.

- Reply sent, status changes, note added, and add-to-pipeline actions trigger safe async reclassification.

- Note-added path performs a fast local signal refresh for revenue, ask, industry, and HELOC fit before the full LLM refresh finishes.

- Manual rep actions that contradict AI classification are logged into classification feedback for future correction corpus.

- Inbound webhook preserves the current active conversation/lead owner before considering the latest active human sender.

- Manual replies in threads with inbound history can bypass quiet hours; cold/manual outreach still enforces quiet hours.

- Inbox AI card/banner render persisted extractedRevenue, extractedAsk, extractedIndustry, and helocFitFlag fallbacks when aiSignals are partial.

- Expanded focused regression passed: AI suggestions, owner reclassification, disagreement feedback, inbound ownership, email policy, follow-up policy, preservation, compliance parser, eligibility, and scoring — 79/79 tests.

- Root production build passed after AI repair changes: server tsc plus client tsc && vite build.

- Production deploy/smoke passed on c30692315: /api/health database/Redis ok, / 200, /login 200, /api/auth/dev-login 404, live login UI dev button count 0.

- Evidence JSON added: audit-screenshots/m14-ai-suggestion-repair-evidence.json.

### Backend foundation

- Add Deal.pipelineAiSignals.

- Add Deal.pipelineAiUpdatedAt.

- Create server/src/services/pipelineAiService.ts parallel to Inbox AI.

- Use exact prompt/schema from scl-pipeline-ai-handoff/scl-pipeline-ai-extractor.md.

- Do not paraphrase prompt/schema/payload contract.

- Use model claude-sonnet-4-5 with prompt caching.

- Use exact payload markers:

  - [EXISTING SIGNALS];

  - [NEW INPUT].

- Use pipeline-ai.fixtures.json as canonical TS test fixture source.

- Keep golden_test_set.json synchronized as standalone reference.

- Implement fallback conversation.aiSignals -> deal.pipelineAiSignals only when appropriate.

- Implement per-deal serialization queue.

- Structured logs include deal id, model, usage, skip reason, duration.

- AI failures never break note save/update.

### Trigger wiring

- Trigger on note_added.

- Trigger on note_updated.

- Trigger on inbound client SMS only for allowed active deal stages.

- Skip on FUNDED, CLOSED, too-short text, unrelated/no-signal conditions.

- Add manual POST /api/ai/extract-pipeline endpoint.

- Resolve remaining behavior: if no saved note exists, re-run uses latest client SMS or disables action.

### Validation

- Port grading logic from run_golden.py into TS tests.

- Use pipeline-golden-results.csv as 15-case baseline.

- Use pipeline-extraction-review.csv as 80-row corpus baseline.

- Track row grade distribution: PERFECT/PARTIAL/FAIL.

- Field-level grading supports PASS/PARTIAL/FAIL.

- Add tests for money tolerance, array set equality, pending action partial matching.

- Add queue serialization tests.

- Add skip-condition tests.

- Add inheritance/merge tests because test_harness.py only validates (none) existing signals.

### Frontend badges and inline bar

- Add PipelineAiSignals type distinct from Inbox AISignals.

- Extend deal API response shape.

- Render industry badge.

- Render monthly revenue badge.

- Render use-of-funds badge.

- Render corrected B.6 stacking chip priority from client update:

  - count >= 3 -> red {N}-STACKED;

  - count === 2 -> orange 2-POSITIONS;

  - count === 1 -> yellow 1-POSITION;

  - has_stacked_history === false && current_active_positions === null -> green 1ST POSITION;

  - recent_stacking_activity.active === true -> red pulse and append · ACTIVE.

- Append · $XXXk to stacking chip when total_debt_usd is set and count >= 2.

- Render AI inline bar in DealPanel above stage/product row.

- Render empty/dashed placeholders where spec requires.

- Render extracted-time/source label.

- Add Re-run AI action loading/error/success states.

- AI suggestions may prefill empty fields visually but must not silently overwrite manual fields.

### M1.4 Testing Gate

- Server build passes after Inbox AI repair gate.

- Inbox AI suggestion policy tests pass for latest-inbound repair, email priority, contextual callbacks, amount disclosures, credit-score objections, fees/rates/payments, and client-email misuse.

- Owner-action reclassification tests pass for reply-sent and unassigned-thread rep fallback.

- Classification disagreement feedback tests pass for rep action vs AI mismatch logging.

- Inbound ownership policy tests pass: current active owner is preserved and unassigned threads fall back to latest active sender.

- Conversation email priority tests pass: texted email -> lead email -> contact email.

- Follow-up policy tests pass for explicit 2-hour windows, exact call times/timezones, next-day noon, and cleared statuses.

- Client preservation tests pass after AI repair gate.

- Pipeline AI unit tests pass.

- Golden tests pass or differences documented with exact fields.

- Note save works when Anthropic API fails.

- Rapid note updates serialize per deal.

- DealCard AI badges render full/partial/empty states.

- DealCard/DealPanel B.6 stacking chip helper compiles for all corrected count states.

- DealCard/DealPanel B.6 stacking chip browser mock renders corrected count states and active pulse modifier.

- DealPanel AI inline bar renders full/partial/empty states.

- Re-run AI tested with note, no-note, API error.

- Pixel-close compare with scl_pipeline_v11.html retained elements.

- Progress dashboard updated for Inbox AI repair gate.

## M1.5 — Auto-Nurture Attempt Mechanic

### Implementation evidence — 2026-05-02

- Added additive Deal fields in Prisma schema: contactAttempts, contactAttemptThreshold, lastEngagementAt.

- Added POST /api/deals/:id/log-attempt backend action.

- Implemented quick-log kinds: no_answer, texted, voicemail, connected, not_interested.

- no_answer, texted, and voicemail increment attempts and write audit metadata.

- connected resets attempts and updates lastEngagementAt.

- not_interested moves deal to NURTURE, sets lost semantics, resets attempts, and does not increment counter.

- Threshold auto-move to NURTURE implemented with audit metadata and linked lead status sync.

- Access control uses existing deal scope policy; funded/closed deals reject quick-log attempts.

- Validation passed: Prisma Client generation, server build, cd server && npx vitest run tests/dealContactAttempts.test.ts tests/dealControllerScope.test.ts tests/dealScopePolicy.test.ts — 14/14 passed.

- Targeted ESLint passed with 0 errors and existing warning debt only.

- Pipeline UI added M1.5 attempt banner on DealCard with WAITING X/Y ATTEMPTS · Z BEFORE AUTO-NURTURE copy and low/mid/near-threshold color states.

- DealPanel added quick-log row using POST /api/deals/:id/log-attempt with No answer/Texted/Voicemail/Connected/Not interested actions.

- Client validation passed: cd client && npm run build.

- Targeted ESLint for DealPanel.tsx still has pre-existing React Compiler errors around old synchronous useEffect state setters/manual memoization; not fixed in this M1.5 UI slice to avoid broad refactor.

- Added inbound SMS engagement reset helper for active deals linked by smsConversationId / leadId, plus matched client deal fallback.

- Added forward stage move reset in moveDeal with engagement_reset audit metadata.

- Validation passed: cd server && npx vitest run tests/dealContactAttempts.test.ts tests/dealControllerScope.test.ts tests/dealScopePolicy.test.ts — 16/16 passed; cd server && npm run build passed; targeted backend ESLint 0 errors / existing warnings only.

- Added admin/manager manual override for contactAttempts reset and contactAttemptThreshold in DealPanel with backend validation and audit metadata.

- Validation passed: focused backend tests 17/17, server build, and client build.

- Browser mock validation passed on production preview: DealCard attempt banner and DealPanel quick-log row rendered for admin with WAITING 3/5, reset changed panel status to WAITING 0/5, and threshold input saved 12.

- Browser UI quick-log buttons exercised from DealPanel: No answer, Texted, Voicemail, Connected, and Not interested buttons all invoked the quick-log flow; backend semantics remain covered by focused Vitest tests.

- Pixel/browser evidence captured in audit-screenshots/m15-attempt-ui-evidence.json; local ignored screenshots generated at audit-screenshots/m15-attempt-ui-desktop.png and audit-screenshots/m15-attempt-ui-mobile.png.

- Quick-log CSS tightened after pixel review: desktop uses compact grid layout; mobile keeps two-column button stack with full-width Not interested.

- Validation passed: cd client && npm run build after quick-log CSS/pixel adjustment.

- Confirmed canonical followUpType values are lowercase UI values; M1.5 auto-threshold now writes reengage instead of snake_case re_engage, while backend label mapping accepts both old and canonical variants.

- Revive Queue compatibility preserved: focused test verifies canonical reengage Nurture follow-up is returned with reviveSource: follow_up.

- Validation passed: focused backend tests 18/18, server build, and targeted ESLint 0 errors / existing warning debt only.

### Data and backend

- Add Deal.contactAttempts default 0.

- Add Deal.contactAttemptThreshold default 10.

- Add Deal.lastEngagementAt.

- Confirm canonical followUpType values/casing for GHOSTED and LOST before implementation.

- Add POST /api/deals/:id/log-attempt.

- Implement quick-log kinds:

  - no answer;

  - texted;

  - voicemail;

  - connected;

  - not interested.

- no_answer, texted, voicemail increment attempts and append auto-note.

- connected resets attempts and updates lastEngagementAt.

- not_interested moves to NURTURE, sets lost semantics, does not increment counter.

- Auto-move to NURTURE at threshold.

- Reset attempts on substantive inbound SMS.

- Reset attempts on connected action.

- Reset attempts on manual forward stage move.

- Reset attempts on manual edit path from B.10.6.

- Every change writes DealEvent audit metadata.

- Revive Queue compatibility preserved.

### UI

- Render quick-log row in DealPanel.

- Render waiting/attempt banner on DealCard.

- Render attempt status in DealPanel.

- Banner text: WAITING X/Y ATTEMPTS · Z BEFORE AUTO-NURTURE.

- Color ratio states:

  - low/yellow;

  - mid/orange;

  - near-threshold/red pulse.

- Quick-log buttons match quick-log-row / ql-btn visual target.

- Attempt banner matches nurture-banner / nu-urg visual target.

- Admin/manager manual override controls added for reset and threshold.

### M1.5 Testing Gate

- Each quick-log action tested by API.

- Each quick-log action tested from UI.

- Threshold auto-move tested.

- Reset on inbound tested.

- Reset on connected tested.

- Reset on forward stage move tested.

- Manual override reset tested.

- Revive Queue still works.

- Pixel-close compare for quick-log row and attempt banner.

- Progress dashboard updated.

## M1.6 — M1 Full Regression And Release Gate

### Initial gate evidence — 2026-05-02

- Evidence JSON added: audit-screenshots/m16-regression-gate-evidence.json.

- Root release build passed: npm run build completed server tsc and client tsc && vite build.

- Full backend suite attempted: cd server && npm test -- --run is blocked by local environment, not by the M1.5 changes. Redis is unavailable on local 6379, and the local Prisma datasource provider does not match the MySQL schema; DB-backed auth and numberService tests cannot complete until a valid MySQL test DB and Redis are available.

- M1.5 focused backend regression remains green: 18/18 focused tests passed before opening M1.6 gate.

- Browser smoke evidence added: audit-screenshots/m16-browser-smoke-evidence.json.

- Production preview + mock API browser smoke passed 4/4: OTP login redirect, Pipeline simple mode, Pipeline execution mode, and DealCard/DealPanel smoke.

- Browser smoke captured no console errors and no request failures inside gate scope; local ignored screenshots were generated for login, simple pipeline, execution pipeline, and deal panel.

### Drag/drop + Funding History smoke — 2026-05-02

- Evidence JSON added: audit-screenshots/m16-drag-funding-evidence.json.

- Drag/drop smoke passed on production preview + mock API: Atlas Demo Logistics moved from Engaged / Interested to Qualified and PUT /api/deals/deal-1/move was captured with {"stage":"QUALIFIED"}.

- Funding History smoke passed: funded deal panel opened, Funding History tab became active, and the existing event showed lender, amount, product, rep, and notes.

- Gate captured no console errors and no request failures inside scope; local ignored screenshots were generated for before-drag, after-drag, and Funding History states.

### Production deploy smoke — 2026-05-02

- Evidence JSON added: audit-screenshots/m16-production-deploy-evidence.json.

- Production dirty state preserved before deploy: worktree backup saved under /root/scl-prod-backups/20260502-175850 and stash pre-deploy-1982fdb-20260502-175850 created.

- Production source fast-forwarded to 1982fdb0 on deploy/mysql-hosting via Git bundle because the droplet has no GitHub deploy key and HTTPS fetch cannot authenticate non-interactively.

- Production DB backup saved under /root/scl-prod-backups/db-20260502180111/database.sql.gz.

- Additive production schema sync verified: OTP user fields, login_otps, deal contact-attempt fields, and contact-attempt indexes are present.

- Production npm run prisma:generate, npm run build, and pm2 restart sms-api --update-env passed; PM2 shows sms-api online.

- Production smoke passed: /api/health returned HTTP 200 with database ok and Redis ok; root HTML returned HTTP 200; browser opened /login and rendered the SCL OTP login screen.

### Inbox AI / Email CTA / Follow-up policy smoke — 2026-05-02

- Evidence JSON added: audit-screenshots/m16-inbox-ai-policy-evidence.json.

- Focused policy tests passed 54/54 across AI suggestion repair, conversation email priority, follow-up parsing, quiet-hours reason formatting, and inbound owner retention.

- Root production build passed after Inbox/AI changes: server tsc plus client tsc && vite build.

- Browser mock smoke passed on fresh production preview: Inbox rendered AI suggestion, texted email Shawnthai@gmail.com, and Gmail CTA generated https://mail.google.com/mail/?view=cm&fs=1&to=Shawnthai%40gmail.com without subject/body.

- Production deploy passed for commit 2f665aaf: build/restart succeeded, /api/health returned HTTP 200 with database ok and Redis ok, root HTML returned HTTP 200, and live login UI rendered.

- Gmail recipient policy prefers conversation/texted email over lead-list email while preserving lead-list email in response metadata.

- Admin/manager self-assign path is allowed only for the current privileged user; ordinary assignment still requires an active REP.

### New deal creation / sharing / socket scoping smoke — 2026-05-02

- Evidence JSON added: audit-screenshots/m16-deal-create-share-socket-evidence.json.

- Backend fix added: shareDeal now emits scoped socket updates from the updated deal record, so newly added assisting reps receive inbox:{repId} updates.

- Focused backend regression passed 14/14 across deal controller scope, deal scope policy, and inbox reply reclassification tests.

- Root production build passed after the backend fix: server tsc plus client tsc && vite build.

- Browser production-preview smoke passed with mock API: created M1.6 Smoke Capital, captured POST /api/deals, shared Atlas Demo Logistics, and captured PUT /api/deals/deal-1/share with assistingRepIds: ["rep-2"].

- Browser screenshot saved: audit-screenshots/m16-deal-create-share-browser-smoke.png.

- Production deploy passed for commit 01b6700d: Git bundle fast-forward, root npm run build, and pm2 restart sms-api --update-env all completed successfully.

- Production smoke passed: /api/health returned HTTP 200 with database ok and Redis ok; root HTML returned HTTP 200; live browser opened /login and rendered the SCL OTP login screen.

### Visual regression smoke — 2026-05-02

- Evidence JSON added: audit-screenshots/m16-visual-regression-evidence.json.

- Desktop 1440px Pipeline screenshot captured and visually reviewed: audit-screenshots/m16-pipeline-desktop-1440.png.

- Half-screen 960px Pipeline screenshot captured and visually reviewed: audit-screenshots/m16-pipeline-half-960.png.

- DealPanel screenshot captured and visually reviewed: audit-screenshots/m16-deal-panel-desktop-1440.png.

- DealCard stacking + attempt banner screenshot captured and visually reviewed: audit-screenshots/m16-deal-card-stacking-attempt.png.

- Playwright DOM audit passed for desktop and half-screen: no document horizontal overflow, no unexpected text overflow, 8 visible columns, 8 visible cards, and layout shift score 0.

- Stacking chip and WAITING 8/10 ATTEMPTS banner remain inside the card; next action row stays below the attempt banner.

- Sidebar/nav links remained unchanged in the visual audit surface.

### Functional regression

- Login/auth full pass.

- Pipeline simple mode pass.

- Pipeline execution mode pass.

- Deal card pass.

- Deal panel pass.

- Drag/drop pass.

- New deal creation pass.

- Deal sharing pass if in current implementation.

- Funding history pass.

- Inbox AI unaffected.

- Email/Gmail CTA unaffected.

- Follow-up timing unaffected.

- Quiet hours unaffected.

- Inbound ownership unaffected.

- Socket scoping unaffected.

### Visual regression

- Desktop 1440px Pipeline screenshot compare.

- Half-screen 960px Pipeline screenshot compare.

- DealPanel screenshot compare.

- DealCard screenshot compare.

- No overlapping text.

- No layout shift when badges/attempt banners appear.

- Sidebar remains unchanged unless intentionally touched.

### Release readiness

- Server tests pass.

- Client build passes.

- Relevant DB migration reviewed as additive.

- Rollback note prepared: source stash/worktree backup and DB dump paths recorded in production deploy evidence.

- Evidence screenshots saved.

- Demo script prepared for JB/client.

- Progress dashboard updated to M1 complete only after all gates pass.

## M2.1 — Leads/Campaign Access And Source Fixes

### Implementation evidence — 2026-05-02

- Affected files: server/src/controllers/leadController.ts, server/src/controllers/campaignController.ts, client/src/pages/LeadsPage.tsx, client/src/pages/CampaignsPage.tsx, server/tests/leadCampaignScope.test.ts.

- Regression surface: Leads list/get/update/import/bulk/tag/export scope; Campaigns list/get/create/update/start/pause/cancel/analytics/sync scope; Campaigns delete UI visibility; Leads Source display fallback.

- Focused tests passed: cd server && npx vitest run tests/leadCampaignScope.test.ts — 5/5 passed.

- Build passed: root npm run build — server tsc + client tsc && vite build.

- Browser smoke passed for admin/rep Leads and Campaigns views with deterministic mocked API evidence: audit-screenshots/m21-m22-leads-campaigns-evidence.json.

- CSV import smoke pending with two real rep accounts.

### Leads ownership bug

- In server/src/controllers/leadController.ts, verify both importCSV and importMappedCSV.

- On REP create, set assignedRepId = req.user.id for newly uploaded leads.

- On ADMIN create, preserve admin/global behavior according to spec.

- On update/upsert existing lead by phone, do not overwrite existing assignedRepId silently.

- Rep Leads tab returns only leads assigned/uploaded by that rep.

- Admin Leads tab returns all leads.

- Manager behavior documented: manager keeps admin-like global visibility for M2.1 unless JB narrows manager scope later.

### Campaign ownership bug

- In server/src/controllers/campaignController.ts, apply rep-scope to list/get/analytics/start/pause/cancel/syncStatuses.

- Rep sees only campaigns where createdById = current_user_id.

- Admin sees all campaigns across reps.

- Rep cannot GET another rep campaign.

- Rep cannot start/pause/cancel/sync another rep campaign.

- ensureRetargetAccess remains compatible.

### Source readable fix

- Leads table Source column shows readable list/campaign name, not UUID.

- Source examples match prototype in deterministic browser smoke:

  - CJ 10.8 12K / Verizon list;

  - FDR Apr / FDR scrubbed;

  - Lead Hoop / Lead Hoop list;

  - Renewal Queue / Renewal · prior.

- Existing UUID-only sources mapped to readable fallback where possible.

- Import flow stores list name as source for future leads.

- Campaign-created leads preserve campaign/list lineage in list/export enrichment logic and browser source smoke.

### M2.1 Testing Gate

- Rep AN uploads CSV -> sees uploaded leads immediately.

- Rep HB cannot see AN leads.

- Admin JB sees all leads.

- Rep AN sees only AN campaigns.

- Rep HB cannot open AN campaign detail.

- Admin JB sees all campaigns.

- Source column before/after checked against prototype.

- API permission tests pass.

- Progress dashboard updated.

## M2.2 — Leads Enrichment Columns And Export CSV

### Implementation evidence — 2026-05-02

- Backend Leads list now returns enrichment for each lead: industry, monthly revenue, revenue source, last contact timestamp, rep initials, contact direction, readable source primary/secondary.

- Enrichment uses existing schema only: Lead.customFields, Deal.client.monthlyRevenue, Conversation.extractedIndustry, Conversation.extractedRevenue, Conversation.aiSignals, latest message attribution, import-list tags, and campaign lineage.

- CSV import mapping now accepts optional Industry, Monthly Revenue, and Annual Revenue fields and stores them in customFields for enrichment/export without a migration.

- Leads table now includes retained M2.2 columns: Last Contact, Industry, Monthly Revenue, Source, Added.

- Leads export button uses current search/status/list filters and downloads /leads/export as CSV blob.

- Export endpoint includes enrichment columns and preserves REP scope.

- Focused tests added in server/tests/leadEnrichmentExport.test.ts for list enrichment and export headers/rows/scope.

- Validation passed: cd server && npx vitest run tests/leadEnrichmentExport.test.ts tests/leadCampaignScope.test.ts — 7/7 passed, with known local Redis ECONNREFUSED warning only.

- Validation passed: root server npm run build; client cd client && npm run build.

- Targeted ESLint passed with 0 errors and existing warning debt only.

### Leads table columns

- Preserve existing Leads page layout and only add retained prototype columns.

- Columns match prototype order:

  - Name;

  - Phone;

  - Status;

  - Last Contact;

  - Industry;

  - Monthly Revenue;

  - Source;

  - Added.

- Last Contact shows rep attribution initials and relative time, e.g. JB 2h ago.

- Industry renders extracted/classified value or — unknown.

- Monthly Revenue renders raw/formatted revenue plus provenance chip:

  - AI;

  - CSV;

  - MANUAL.

- Empty revenue renders —.

- Source cell uses two-line readable source/list pattern.

- Status pill styles checked in browser smoke with retained table/card rendering.

- Avatar initials checked in browser smoke with retained table/card rendering.

### Data plumbing

- Confirm data source for industry:

  - existing AI classifier field;

  - CSV value;

  - manual override.

- Confirm data source for monthly revenue:

  - existing AI extraction;

  - CSV import;

  - manual field.

- Define priority when values conflict: manual > CSV > AI unless spec says otherwise.

- Last Contact uses latest meaningful contact and preserves admin attribution.

- Rep scope applies to all enrichment queries.

### Export CSV

- Export button label includes filtered count, e.g. Export CSV 12 leads.

- Export respects current search.

- Export respects status filter.

- Export respects list/source filter.

- Export respects rep scope.

- Export includes new columns:

  - last contact;

  - last contact rep;

  - industry;

  - monthly revenue;

  - revenue source;

  - readable source/list.

- Export does not leak admin-only or other-rep leads to rep user.

- CSV escaping handles commas, quotes, line breaks.

### M2.2 style isolation

- Existing styles apply correctly to new columns in desktop and responsive browser smoke.

- No scoped Leads/Campaigns style set needed after smoke; existing overflow-safe styles held.

- Do not modify sidebar layout/classes for this section.

- Verify table remains readable at desktop and half-screen widths by fixed min-width/overflow-safe columns.

- Ensure text truncation/line wrapping is deliberate and not overlapping.

### M2.2 Testing Gate

- Admin Leads table matches retained prototype scope in browser smoke.

- Rep Leads table matches retained prototype scope with scoped data in browser smoke.

- Last Contact values checked against deterministic mocked API data and controller enrichment tests.

- Industry/revenue values checked against classifier/manual/CSV source precedence in focused controller tests.

- Export CSV checked with filters in focused controller test.

- Export CSV opened/verified by focused controller test and mocked browser export route; columns recorded in evidence.

- Pixel-close compare with Leads prototype.

- Progress dashboard updated.

## M2.3 — AI Retarget Campaigns

### Implementation evidence — 2026-05-02

- Added live AI cohort API foundation without DB migration: GET /api/campaigns/ai-cohorts, GET /api/campaigns/ai-cohorts/:cohortId/preview, POST /api/campaigns/ai-cohorts/:cohortId/build.

- Added three deterministic analytical cohort engines: multi-retarget, new restaurants, and admin-only renewals.

- Cohort queries exclude deleted, opted-out, suppressed, and DNC leads and apply rep lead scope for REP users.

- Cooldowns are applied before count/build: 7 days for multi-retarget/new cohorts, 30 days for renewals.

- AI cohort build creates a DRAFT campaign only; it does not auto-send or queue SMS.

- AI-built campaign lineage is stored through existing Campaign.description + isRetarget fields and surfaced as AI Cohort · N leads · ~X funded expected.

- Campaigns UI now renders AI Retarget Suggestions above All Campaigns, preview modal, Build Campaign action, AI badge, and lineage marker.

- Focused tests added in server/tests/campaignAiCohorts.test.ts for admin cohorts, REP renewal exclusion, and draft campaign build.

- Validation passed: cd server && npx vitest run tests/campaignAiCohorts.test.ts tests/leadCampaignScope.test.ts tests/leadEnrichmentExport.test.ts — 10/10 passed, with known local Redis ECONNREFUSED warning only.

- Validation passed: root npm run build including server and client build.

- Targeted ESLint passed with 0 errors and existing warning debt only.

- Cap edge coverage added: REP per-campaign trim to 500 and rolling 24h daily cap exhaustion error with requested/cap/dailyUsed/remaining details.

- Validation passed: cd server && npx vitest run tests/campaignAiCohorts.test.ts — 5/5 passed after cap tests; server build passed.

### Implementation evidence — 2026-05-04

- Added Prisma LeadCohort model mapped to lead_cohorts with user, cohort type, title/description, query JSON, source attribution, predicted reply rate, expected funded count, historical anchor, AI reasoning, match/eligible/resolved counts, cap metadata, warnings, sample leads, lead IDs, and 24h expiry.

- Added active cache lookup for AI cohort reasoning using expiresAt > now; expired snapshots are ignored safely.

- Added Anthropic Claude Sonnet 4.5 reasoning path for cohorts with deterministic fallback when Anthropic key is missing.

- Reasoning prompt includes filter criteria, anonymized sample leads, funded-history aggregate, counts, and current capacity.

- Added 15-minute AI cohort cron wired into server startup and graceful shutdown.

- Cron runs across active ADMIN/MANAGER/REP users and isolates failures per user/cohort.

- Focused tests added/expanded in server/tests/campaignAiCohorts.test.ts and server/tests/aiCohortCron.test.ts for cache hit, cache miss snapshot write, expired-cache ignore, Anthropic reasoning input, and cron failure isolation.

- Campaigns UI Build Campaign now opens the existing campaign modal with AI cohort name, message template, and resolved lead set preloaded while preserving the AI build endpoint for lineage.

- Mocked browser smoke passed for AI Build modal preload, submit, AI-built campaign list appearance, AI badge, lineage marker, and no horizontal overflow.

- Mocked browser regression passed for existing Campaign actions: retarget preview/create/lineage, start, pause, cancel, delete, status updates, deleted-row removal, and no horizontal overflow.

- Validation passed: cd server && npx vitest run tests/campaignAiCohorts.test.ts tests/aiCohortCron.test.ts — 8/8 passed, with known local Redis ECONNREFUSED warning only.

- Validation passed: cd client && npm run build after Campaigns modal flow change.

- Validation passed: npm run build — server tsc, client tsc, and Vite production build passed.

- Production deploy completed on https://app.sclcapital.io/ with MySQL backup, additive lead_cohorts table creation, Prisma generate, PM2 restart, API health, dev-login 404 guard, new frontend asset, and leadCohort.count() smoke.

- Prisma db push was not forced with --accept-data-loss; unrelated varchar warnings were avoided by manual additive SQL for lead_cohorts only.

- Campaigns v3 prototype retained-scope compare passed: AI Retarget Suggestions, 3 cohort cards, All Campaigns, AI badge, lineage marker, no suppressed/list-management/cohort-bar scope creep, desktop/mobile no-overflow, and screenshots saved.

- VS Code problems check passed with 0 errors for changed M2.3 files.

- Evidence recorded: audit-screenshots/m23-ai-cohort-cache-cron-evidence.json.

### Scope lock for AI Retarget

- Confirm current scope follows v3 prototype Phase 3 only.

- Do not add suppressed leads zone, list management, multi-owner, or extra cohort bar.

- Admin view can build all-campaigns cohorts.

- Rep view behavior respects createdBy/ownership rules.

- Treat Phase 3 as data intelligence pipeline, not UI-only work.

- Confirm Phase 1 access fixes are complete before Phase 3 cohort generation:

  - lead assignedRepId correctness;

  - campaign createdById scoping correctness.

### Database model

- Add lead_cohorts / LeadCohort model if not already present.

- Store userId.

- Store cohortType: multi-retarget / new cohort / renewal.

- Store title and description.

- Store query JSON or resolved criteria metadata.

- Store source campaigns/source attribution.

- Store predicted reply rate.

- Store predicted funded deals / expected funded count.

- Store historical anchor line data.

- Store AI reasoning.

- Store resolved lead count.

- Store total match count and cap-trim metadata.

- Store daily remaining capacity at generation.

- Store expiresAt around 24h.

- Add indexes for user/expiry and active cohort lookup.

- Ensure expired cohorts are ignored safely.

### Cohort generation

- Build/verify all-campaigns cohort source across relevant past campaigns.

- Generate Cross-rep retarget — replied with $80K+ revenue, stalled at docs style cohort.

- Generate Restaurants · $80K+ rev · never contacted across all rep imports style cohort.

- Generate Funded 8-12 mo ago · likely renewals · admin-only style cohort.

- Implement three separate analytical query engines:

  - multi-campaign retarget;

  - new cohorts from unsent leads;

  - renewal candidates.

- Each query joins only the required campaign/lead/funded/deal data and remains performant.

- Each cohort includes:

  - lead count;

  - predicted reply rate;

  - expected funded deals;

  - historical anchor line;

  - AI reasoning line;

  - override/cooldown warning when applicable.

- Exclude opted-out, DNC, suppressed leads.

- Respect recent retarget cooldown and admin override warning semantics.

- Ensure predicted funded deals are traceable to historical anchor, not arbitrary text.

### Cooldowns and compliance

- Enforce 7-day cooldown for multi-retarget and new cohort contact history.

- Enforce 30-day cooldown for renewal candidates.

- Track contact event timestamps across all campaigns for each lead.

- Surface cooldown countdown/override warning in UI where prototype expects it.

- Ensure cooldown logic applies before cohort count and before campaign build.

- Verify no cohort can re-contact opted-out, DNC, suppressed, or too-recent leads.

### Two-layer send caps

- Enforce per-campaign cap server-side for AI cohort build:

  - rep: 500;

  - admin: 3000.

- Enforce rolling 24-hour daily total cap server-side for AI cohort build:

  - rep: 800;

  - admin: 4500.

- Daily total uses rolling 24h window, not calendar day reset.

- Cap errors include requested/cap/role/dailyUsed/remaining details.

- UI displays current daily capacity and nearly-full state.

- Cohort card lead count reflects current remaining capacity at render/build time.

### AI reasoning and cron

- Use Anthropic Claude Sonnet 4.5 for cohort reasoning.

- Reasoning prompt includes filter criteria, anonymized sample leads, and funded history aggregates.

- Reasoning output is 1-2 business-specific sentences, not generic boilerplate.

- Cache reasoning for 24h.

- Scheduled job runs every 15 minutes.

- Cron runs per user: admin + each active rep.

- Cron is non-blocking, idempotent, and failure-tolerant.

- Cron handles 8 users x 3 cohorts without blocking API/server responsiveness.

- Log failures per user/cohort without breaking other cohorts.

### UI

- AI Retarget Suggestions section appears above All Campaigns list.

- Section subtitle shows all-reps campaign base and refresh time.

- Three cards render with correct priority labels.

- Cards show live capacity data.

- Cards show cohort-trim messaging when cap is lower than match count.

- Cards show daily capacity nearly full messaging.

- Preview button opens intended preview flow or documented placeholder.

- Build Campaign opens existing New Campaign modal with preloaded lead set.

- AI-built campaigns appear in All Campaigns table.

- AI-built campaigns show AI badge.

- AI-built campaigns show lineage marker, e.g. ↻ from AI Cohort · 487 leads · ~6 funded expected.

- Existing campaign actions still work: rerun/refresh, start, pause, delete where allowed.

### Backend/API

- Add/verify endpoint for AI cohorts.

- Add/verify endpoint to resolve cohort to lead ids.

- Ensure cohort build does not bypass campaign caps or compliance guards.

- Ensure build campaign path uses existing campaign creation validation.

- Ensure created campaign stores lineage metadata.

- Ensure rep users cannot use admin-only renewal/cross-rep cohorts unless explicitly allowed.

- Existing campaign send path remains unchanged downstream of preloaded leads.

- AI Retarget is upstream recommendation only; no auto-send.

### M2.3 Testing Gate

- Admin sees all 3 AI Retarget cohorts in focused API test.

- Rep sees only allowed/scoped cohorts in focused API test.

- Preview flow tested in focused controller test.

- Build Campaign flow tested in focused API test.

- New AI-built campaign appears in All Campaigns list in mocked browser smoke.

- Lineage marker verified in mocked browser smoke.

- Cooldown/override warning verified in focused API test.

- Compliance exclusions verified by query constraints and focused build/list tests.

- Per-campaign caps tested for rep path.

- Rolling 24h daily caps tested for rep path.

- Expired cohorts ignored after 24h.

- Cron failure for one cohort does not break other cohorts.

- AI reasoning is cached and not regenerated unnecessarily.

- Pixel-close compare with Campaigns prototype for retained M2.3 scope; full shell-wide pixel-perfect match is not claimed because app chrome is outside this retained prototype slice.

- Progress dashboard updated.

## M2.4 — M2 Full Regression And Release Gate

### Functional regression

- Leads import still works.

- Add Lead still works.

- Existing Leads search works.

- Existing Status filter works.

- Existing Lists filter works.

- Campaign list search works.

- Campaign status filter works.

- New Campaign modal still works.

- Campaign start/pause/cancel actions still work.

- Campaign analytics/detail still works.

- Inbox reply/campaign reply linking still works.

- Retarget suppression still works.

- Template guards still block unresolved {{...}} and test messages.

### Regression bootstrap evidence — 2026-05-04

- Focused M2 backend regression passed: leadCampaignScope, leadEnrichmentExport, campaignAiCohorts, aiCohortCron — 4 files / 15 tests.

- Root build passed: server tsc, client tsc, Vite production build.

- Mocked Leads UI smoke passed for render, search reload, Export CSV endpoint call, Import modal open, Add Lead modal open, enrichment visibility, and desktop no-overflow.

- Mocked Campaigns UI smoke passed for render, search reload, New Campaign modal, AI Retarget visibility, and Start/Pause/Cancel endpoint calls using visible action buttons.

- Extended Leads UI smoke passed for status/list filters, Add Lead submit payload, CSV preview, and mapped CSV import.

- Extended Campaigns UI smoke passed for status filter and Create Campaign submit with selected list filterTags.

- Evidence JSON saved: audit-screenshots/m24-regression-bootstrap-evidence.json.

### Visual regression

- Leads admin screenshot pixel-close compared to prototype.

- Leads rep screenshot pixel-close compared to prototype after switching Rep view (HB) equivalent.

- Campaigns admin screenshot pixel-close compared to prototype.

- Campaigns rep screenshot pixel-close compared to prototype.

- Sidebar/menu unchanged.

- No table overflow at half-screen width.

- Buttons/icons match prototype density and spacing.

- No unreadable text if current styles fail; scoped style set added if needed.

### Release readiness

- Server tests pass.

- Client build passes.

- Browser smoke pass for Leads.

- Browser smoke pass for Campaigns.

- Export CSV smoke pass.

- Permission negative cases pass.

- Evidence screenshots saved.

- Demo script prepared for JB/client.

- Progress dashboard updated to M2 complete only after all gates pass.

## Full Final Acceptance

- Overall progress dashboard shows 100% only after M1 and M2 release gates pass.

- M1 Login/Auth works for admin and rep.

- M1 Pipeline v2 works with correct data isolation and no stage/metric regression.

- M1 Pipeline AI badges and auto-nurture behavior match confirmed scope.

- M2 Leads table matches v3 prototype scope.

- M2 Campaigns AI Retarget matches v3 prototype scope.

- Side menu remains unaffected.

- No hidden scope creep from older docs is shipped without approval.

- Pixel-close evidence exists for all retained prototype elements.

- Regression evidence exists for all previously painful client issues.

- Final client-facing summary prepared with what changed, how it was tested, and what is intentionally out of scope.

## Progress Update Log

| Date | Progress | Area | What changed | Evidence |
| --- | --- | --- | --- | --- |
| 2026-05-02 | 71% | M1.6 | Added drag/drop + Funding History smoke evidence; moved M1.6 from 3/8 to 4/8 while keeping full-env/release gates open. | audit-screenshots/m16-drag-funding-evidence.json |
| 2026-05-02 | 72% | M1.6 | Deployed 1982fdb0 to https://app.sclcapital.io/, applied additive DB schema sync, rebuilt/restarted PM2, and passed production smoke. | audit-screenshots/m16-production-deploy-evidence.json |
| 2026-05-02 | 73% | M1.6 | Added and deployed Inbox AI/email CTA/follow-up/quiet-hours/inbound-owner regression evidence; production smoke passed on 2f665aaf. | audit-screenshots/m16-inbox-ai-policy-evidence.json |
| 2026-05-02 | 74% | M1.6 | Added and deployed new deal creation/sharing/socket scoping evidence; production smoke passed on 01b6700d. | audit-screenshots/m16-deal-create-share-socket-evidence.json |
| 2026-05-02 | 75% | M1.6 | Added visual regression evidence for Pipeline 1440/960, DealPanel, DealCard, overlap/layout-shift, and sidebar checks. | audit-screenshots/m16-visual-regression-evidence.json |
| 2026-05-04 | 76% | M1.4/M1.6 | Locked angry-client preservation requirements, restored Inbox Mark Unread/Note in action row, tightened login visual fit, and passed focused tests/build/prod access smoke. | audit-screenshots/client-preservation-login-access-evidence.json |
| 2026-05-04 | 77% | M1.1 | Added and deployed safe dev-only login without OTP for local QA, with production backend/frontend guards, focused auth tests, build, and live smoke evidence. | audit-screenshots/dev-mode-login-evidence.json |
| 2026-05-04 | 80% | M1.4 | Added and deployed Inbox AI latest-inbound repair, email priority, owner-action reclassification, inbound owner preservation, quiet-hours reply bypass, and live smoke evidence. | audit-screenshots/m14-ai-suggestion-repair-evidence.json |
| 2026-05-04 | 82% | M2.1/M2.2 | Closed lead/campaign scope, readable source, enrichment/export, admin/rep browser smoke, and responsive overflow evidence; live two-rep CSV smoke and strict pixel-close remain. | audit-screenshots/m21-m22-leads-campaigns-evidence.json |
| 2026-05-04 | 84% | M2.3 | Added LeadCohort DB/cache, Sonnet reasoning, cron, Build modal/list/actions smoke, tests/build, and production DB/health/frontend smoke. | audit-screenshots/m23-ai-cohort-cache-cron-evidence.json |
| 2026-05-04 | 84.5% | M1.1 | Passed live SMS OTP delivery, verify, consumed-code, /auth/me, browser redirect, and dev-login production guard; Resend email fallback remains blocked by missing env config. | audit-screenshots/m11-live-otp-evidence.json |
| 2026-05-04 | 85.5% | M2.3 | Closed retained Campaigns prototype compare with saved screenshots for AI Retarget cards, All Campaigns, AI badge/lineage, no scope creep, and desktop/mobile no-overflow. | audit-screenshots/m23-ai-cohort-cache-cron-evidence.json |
| 2026-05-04 | 87.5% | M2.4 | Passed M2 functional regression bootstrap: focused backend tests 15/15, root build, mocked UI smoke for search/filters/import/add/export/create/actions; deeper gates remain. | audit-screenshots/m24-regression-bootstrap-evidence.json |
| 2026-05-02 | 6% | Planning | Consolidated M1/M2 sources, previous checklists, Pipeline v11 handoff, and Leads/Campaigns v3 prototype into one master checklist. | This file |